## WBS & GANTT
FPGA/3D Modeling feature on 3DViewer - tracking list
Working Schedule
by FPGA/tvq_huy at Brycen Vietnam, 2020
※ unauthorized use any content in this document is prohibited | +
WBS ID | WBS Level | TASK LIST (major tasks: WBS level 1-2, minor tasks: WBS level 3-4) | PROGRESS TRACKING |  |  |  | October | [30 empty] | November | [29 empty] | December
|  |  | start date yyyy/mm/dd | due date yyyy/mm/dd | progress % | status | 2020-10-01 | 2020-10-02 | 2020-10-03 | 2020-10-04 | 2020-10-05 | 2020-10-06 | 2020-10-07 | 2020-10-08 | 2020-10-09 | 2020-10-10 | 2020-10-11 | 2020-10-12 | 2020-10-13 | 2020-10-14 | 2020-10-15 | 2020-10-16 | 2020-10-17 | 2020-10-18 | 2020-10-19 | 2020-10-20 | 2020-10-21 | 2020-10-22 | 2020-10-23 | 2020-10-24 | 2020-10-25 | 2020-10-26 | 2020-10-27 | 2020-10-28 | 2020-10-29 | 2020-10-30 | 2020-10-31 | 2020-11-01 | 2020-11-02 | 2020-11-03 | 2020-11-04 | 2020-11-05 | 2020-11-06 | 2020-11-07 | 2020-11-08 | 2020-11-09 | 2020-11-10 | 2020-11-11 | 2020-11-12 | 2020-11-13 | 2020-11-14 | 2020-11-15 | 2020-11-16 | 2020-11-17 | 2020-11-18 | 2020-11-19 | 2020-11-20 | 2020-11-21 | 2020-11-22 | 2020-11-23 | 2020-11-24 | 2020-11-25 | 2020-11-26 | 2020-11-27 | 2020-11-28 | 2020-11-29 | 2020-11-30 | 2020-12-01 | 2020-12-02 | 2020-12-03 | 2020-12-04 | 2020-12-05 | 2020-12-06 | 2020-12-07 | 2020-12-08 | 2020-12-09 | 2020-12-10 | 2020-12-11 | 2020-12-12 | 2020-12-13 | 2020-12-14 | 2020-12-15 | 2020-12-16 | 2020-12-17 | 2020-12-18 | 2020-12-19 | 2020-12-20 | 2020-12-21 | 2020-12-22 | 2020-12-23 | 2020-12-24 | 2020-12-25 | 2020-12-26 | 2020-12-27 | 2020-12-28 | 2020-12-29 | 2020-12-30 | 2020-12-31
1 | 1 | Đọc tài liệu 3D Modeling | 2020-10-08 | 2020-08-13
1.1 | 2 | Đọc speification từ anh Cường | 2020-10-08 | 2020-10-08
1.1.1 | 3 | Đọc tổng quan và nắm bắt ý chính. | 2020-10-08 | 2020-10-08 | 100% | Done
1.1.2 | 3 | Đọc chi tiết từng mục nhỏ. | 2020-10-08 | 2020-10-08 | 100% | Done
1.1.3 | 3 | Tìm kiếm tài liệu liên quan để hiểu hơn về chức năng. | 2020-10-08 | 2020-10-08 | 40%
1.2 | 2 | Đọc tài liệu về xây dựng UI và luồng xử lý | 2020-10-09 | 2020-10-09
1.2.1 | 3 | Tìm hiểu bố cục và thứ tự hiển thị của các giao diện. | 2020-10-09 | 2020-10-09 | 100% | Done
1.2.2 | 3 | Hiểu và nắm bắt luồng dữ liệu được xử lý. | 2020-10-09 | 2020-10-09 | 100% | Done
2 | 1 | Code giao diện cho 3DViewer. | 2020-10-12
2.1 | 2 | Tùy chỉnh giao diện tĩnh | 2020-10-13 | 2020-10-14
2.1.1 | 3 | Thêm các giao diện từ UI-2 đến UI-5. | 2020-10-13 | 2020-10-13 | 100% | Done
2.1.2 | 3 | Thêm các giao diện từ UI-6 đến UI-9. | 2020-10-14 | 2020-10-14 | 100% | Done
2.2 | 2 | Thêm các sự kiện cơ bản | 2020-10-15 | 2020-10-16
2.2.1 | 3 | Thêm sự kiện cơ bản các giao diện từ UI-2 đến UI-5. | 2020-10-15 | 2020-10-15 | 95%
2.2.2 | 3 | Thêm sự kiện cơ bản các giao diện từ UI-6 đến UI-9. | 2020-10-16 | 2020-10-16 | 95%
2.3 | 2 | Triển khai chức năng chính trong giao diện | 2020-10-19 | 2020-11-09
2.3.1 | 3 | Bắt đầu quá trình scan. | 2020-10-19 | 2020-10-27
2.3.1.1 | 4 | Kiểm tra và thông báo lỗi. | 2020-10-19 | 2020-10-20
2.3.1.2 | 4 | Xử lý với dữ liệu đầu vào. | 2020-10-21 | 2020-10-22
2.3.1.3 | 4 | Xử lý sau khi quá trình scan hoàn tất. | 2020-10-23 | 2020-10-26
2.3.1.4 | 4 | Dừng trong quá trình scan. | 2020-10-27 | 2020-10-27
2.3.2 | 3 | Kết thúc quá trình scan. | 2020-10-28 | 2020-11-04
2.3.2.1 | 4 | Lưu với dạng polygon data. | 2020-10-28 | 2020-10-30
2.3.2.2 | 4 | Lưu với dạng point cloud data. | 2020-11-02 | 2020-11-03
2.3.2.3 | 4 | Trở về hoặc thoát. | 2020-11-04 | 2020-11-04
2.3.3 | 3 | Chạy thử và tinh chỉnh | 2020-11-05 | 2020-11-05
2.3.4 | 3 | Làm sạch code và rà soát lỗi | 2020-11-06 | 2020-11-09
3 | 1 | Viết tài liệu | 2020-11-09 | 2020-11-18
3.1 | 2 | Viết test case. | 2020-11-10 | 2020-11-17
3.1.1 | 3 | Xác các chức năng và trường hợp test | 2020-11-10 | 2020-11-11
3.1.2 | 3 | Tiến hành test cho từng trường hợp và ghi lại kết quả. | 2020-11-12 | 2020-11-12
3.1.3 | 3 | Khắc phục các lỗi được phát hiện. | 2020-11-13 | 2020-11-17
3.2 | 2 | Viết tài liệu cho chức năng. | 2020-11-18 | 2020-11-19
3.2.2 | 3 | Viết và chỉnh sửa các tài liệu liên quan | 2020-11-18 | 2020-11-19