## WBS & GANTT
FPGA/WBS - tracking list
※ unauthorized use any content in this document is prohibited
Refer to the requirement definition sheet https://cb.brycen.co.jp/cgi-bin/cbag/ag.cgi?page=FileView&ffid=490126
WBS ID | WBS Level | TASK LIST (major tasks: WBS level 1-2, minor tasks: WBS level 3-4) | PROGRESS TRACKING |  |  |  | AUGUST | [30 empty] | September
|  |  | start date yyyy/mm/dd | due date yyyy/mm/dd | progress % | status | 1899-12-31 00:06 | 1900-01-01 00:06 | 1900-01-02 00:06 | 1900-01-03 00:06 | 1900-01-04 00:06 | 1900-01-05 00:06 | 1900-01-06 00:06 | 1900-01-07 00:06 | 1900-01-08 00:06 | 1900-01-09 00:06 | 1900-01-10 00:06 | 1900-01-11 00:06 | 1900-01-12 00:06 | 1900-01-13 00:06 | 1900-01-14 00:06 | 1900-01-15 00:06 | 1900-01-16 00:06 | 1900-01-17 00:06 | 1900-01-18 00:06 | 1900-01-19 00:06 | 1900-01-20 00:06 | 1900-01-21 00:06 | 1900-01-22 00:06 | 1900-01-23 00:06 | 1900-01-24 00:06 | 1900-01-25 00:06 | 1900-01-26 00:06 | 1900-01-27 00:06 | 1900-01-28 00:06 | 1900-01-29 00:06 | 1900-01-30 00:06 | 1900-01-31 00:06 | 1900-02-01 00:06 | 1900-02-02 00:06 | 1900-02-03 00:06 | 1900-02-04 00:06 | 1900-02-05 00:06 | 1900-02-06 00:06 | 1900-02-07 00:06 | 1900-02-08 00:06 | 1900-02-09 00:06 | 1900-02-10 00:06 | 1900-02-11 00:06 | 1900-02-12 00:06 | 1900-02-13 00:06 | 1900-02-14 00:06 | 1900-02-15 00:06 | 1900-02-16 00:06 | 1900-02-17 00:06 | 1900-02-18 00:06 | 1900-02-19 00:06 | 1900-02-20 00:06 | 1900-02-21 00:06 | 1900-02-22 00:06 | 1900-02-23 00:06 | 1900-02-24 00:06 | 1900-02-25 00:06 | 1900-02-26 00:06 | 1900-02-27 00:06 | 1900-02-28 00:06 | 1900-03-01 00:06
1 | 1 | Viết tài liệu phân tích thiết kế hệ thống. | 2020-08-10 | 2020-08-13
1.1 | 2 | Khảo sát, phân tích nghiệp vụ. | 2020-08-10 | 2020-08-11
1.1.1 | 3 | Tìm hiểu yêu cầu và mục địch của người dùng. | 2020-08-10 | 2020-08-10
1.1.2 | 3 | Phân tích và lựa chọn phương pháp. | 2020-08-11 | 2020-08-11
1.1.3 | 3 | Đánh giá và xây dựng cấu tài liệu. | 2020-08-11 | 2020-08-11
1.2 | 2 | Tìm hiểu công nghệ, thiết kế sơ đồ và hoàn thành nội dung. | 2020-08-12 | 2020-08-13
2.1.1 | 3 | Đánh giá và lựa chọn công nghệ phù hợp với nhu cầu ứng dụng. | 2020-08-12 | 2020-08-12
2.1.2 | 3 | Vẽ sơ đồ kết cấu và luồng thực thi của ứng dụng. | 2020-08-12 | 2020-08-12
2.1.3 | 3 | Sắp xếp theo bố cục và hoàn thành nội dung. | 2020-08-13 | 2020-08-13
2 | 1 | Tiến hành huấn luyện các ký tự cần sử dụng trong ứng dụng. | 2020-08-17 | 2020-09-07
2.1 | 2 | Thu thập dữ liệu. | 2020-08-17 | 2020-08-24
2.1.1 | 3 | Đánh giá dữ liệu. | 2020-08-17 | 2020-08-18
2.1.2 | 3 | Tìm kiếm và thu thập các dữ liệu đặc trưng cho bộ dữ liệu kiểm tra. | 2020-08-18 | 2020-08-24
2.2 | 2 | Tiền xử lý dữ liệu. | 2020-08-25 | 2020-08-29
2.2.1 | 3 | Loại bỏ dữ liệu trùng lặp. | 2020-08-25 | 2020-08-25
2.2.2 | 3 | Sử dụng một số phép biến đổi để tăng dữ liệu. | 2020-08-26 | 2020-08-28
2.2.3 | 3 | Làm mịn và điều chỉnh kích thước ảnh. | 2020-08-29 | 2020-08-29
2.2.4 | 3 | Phân chia theo cấu trúc | 2020-08-29 | 2020-08-29
2.3 | 2 | Huấn luyện mô hình | 2020-08-30 | 2020-09-04
2.3.1 | 3 | Thiết lập cách nạp dữ liệu vào mô hình. | 2020-08-30 | 2020-08-30
2.3.2 | 3 | Thiết kế mô hình. | 2020-08-31 | 2020-08-31
2.3.3 | 3 | Thiết lập các siêu tham số mô hình. | 2020-09-01 | 2020-09-03
2.3.4 | 3 | Đánh giá nhanh kết quả. | 2020-09-03 | 2020-09-03
2.3.5 | 3 | Tinh chỉnh và thay đổi mô hình trong quá trình huấn luyện. | 2020-09-03 | 2020-09-04
2.4 | 2 | Đánh giá khi hoàn thành và lưu mô hình. | 2020-09-05 | 2020-09-10
2.4.1 | 3 | Hiển thị kết quả độ chính xác trên hai bộ dữ liệu đánh giá và kiểm tra. | 2020-09-05 | 2020-09-05
2.4.2 | 3 | Đánh giá mô hình dựa trên ma trận nhầm lẫn. | 2020-09-06 | 2020-09-06
2.4.3 | 3 | Đánh giá lại mô hình. | 2020-09-07 | 2020-09-08
2.4.3.1 | 4 | Quay lại tinh chỉnh mô hình theo kết quả đánh giá. | 2020-09-08 | 2020-09-09
2.4.3.2 | 4 | Lưu mô hình nếu đủ điều kiện. | 2020-09-08 | 2020-09-09
2.4.4 | 3 | Lựa chọn mô hình và kiểm thử khi chạy thực tế. | 2020-09-09 | 2020-09-10
3 | 1 | Kết nối ký tự điều khiển đầu ra với ứng dụng | 2020-09-11 | 2020-09-27
3.1 | 2 | Tìm hiểu và xác định phương pháp | 2020-09-11 | 2020-09-14
3.2.1 | 3 | Chuyển đổi đầu ra của mô hình thành ký tự truyền đi. | 2020-09-11 | 2020-09-11
3.2.2 | 3 | Tìm hiểu cách điều khiển bàn phím với ký tự tương ứng. | 2020-09-12 | 2020-09-13
3.2.3 | 3 | Tìm hiểu về cách giao tiếp giữa các ứng dụng và độ trễ khi truyền tín hiệu. | 2020-09-13 | 2020-09-14
3.2 | 2 | Triển khai code và tiến hành debug | 2020-09-14 | 2020-09-27
3.2.1 | 3 | Thiết lập kết nối gửi nhận tính hiệu. | 2020-09-14 | 2020-09-14
3.2.2 | 3 | Focus được vào đúng ứng dụng muốn điều khiển. | 2020-09-15 | 2020-09-16
3.2.2.1 | 4 | Đọc thông tin về ứng dụng trong hệ thống. | 2020-09-17 | 2020-09-18
3.2.2.2 | 4 | Xử lý với để ký tự điều khiển focus vào đúng ứng dụng. | 2020-09-18 | 2020-09-18
3.2.2.3 | 4 | Xử lý tình huống không focus đúng ứng dụng. | 2020-09-19 | 2020-09-20
3.2.3 | 3 | Kiểm tra các chức năng xem đã hoạt đúng theo yêu cầu. | 2020-09-21 | 2020-09-22
3.2.4 | 3 | Đánh giá tốc độ. | 2020-09-23 | 2020-09-27
4 | 1 | Tăng độ chính xác của các cử chỉ điều khiển chuột bằng phương pháp theo dấu bàn tay. | 2020-09-28 | 2020-10-10
4.1 | 2 | Tìm kiếm và thu thập tài liệu liên quan.
4.2 | 3 | Thử nghiệm, đánh giá và lựa chọn phương pháp.