## WBS & GANTT
FPGA/Thao tác trên 3DViewer bằng cử chỉ - tracking list
Working Schedule
by FPGA/tvq_huy at Brycen Vietnam, 2020
※ unauthorized use any content in this document is prohibited
WBS ID | WBS Level | TASK LIST (major tasks: WBS level 1-2, minor tasks: WBS level 3-4) | PROGRESS TRACKING |  |  |  | AUGUST | [30 empty] | September
|  |  | start date yyyy/mm/dd | due date yyyy/mm/dd | progress % | status | 2020-08-01 | 2020-08-02 | 2020-08-03 | 2020-08-04 | 2020-08-05 | 2020-08-06 | 2020-08-07 | 2020-08-08 | 2020-08-09 | 2020-08-10 | 2020-08-11 | 2020-08-12 | 2020-08-13 | 2020-08-14 | 2020-08-15 | 2020-08-16 | 2020-08-17 | 2020-08-18 | 2020-08-19 | 2020-08-20 | 2020-08-21 | 2020-08-22 | 2020-08-23 | 2020-08-24 | 2020-08-25 | 2020-08-26 | 2020-08-27 | 2020-08-28 | 2020-08-29 | 2020-08-30 | 2020-08-31 | 2020-09-01 | 2020-09-02 | 2020-09-03 | 2020-09-04 | 2020-09-05 | 2020-09-06 | 2020-09-07 | 2020-09-08 | 2020-09-09 | 2020-09-10 | 2020-09-11 | 2020-09-12 | 2020-09-13 | 2020-09-14 | 2020-09-15 | 2020-09-16 | 2020-09-17 | 2020-09-18 | 2020-09-19 | 2020-09-20 | 2020-09-21 | 2020-09-22 | 2020-09-23 | 2020-09-24 | 2020-09-25 | 2020-09-26 | 2020-09-27 | 2020-09-28 | 2020-09-29 | 2020-09-30
1 | 1 | Viết tài liệu phân tích thiết kế hệ thống. | 2020-08-10 | 2020-08-13
1.1 | 2 | Khảo sát, phân tích nghiệp vụ. | 2020-08-10 | 2020-08-11
1.1.1 | 3 | Tìm hiểu yêu cầu và mục đích của người dùng. | 2020-08-10 | 2020-08-10 | 100% | Done
1.1.2 | 3 | Phân tích và lựa chọn phương pháp. | 2020-08-11 | 2020-08-11 | 100% | Done
1.1.3 | 3 | Đánh giá và xây dựng cấu trúc tài liệu. | 2020-08-11 | 2020-08-11 | 100% | Done
1.2 | 2 | Tìm hiểu phương pháp, thiết kế sơ đồ và hoàn thành nội dung. | 2020-08-12 | 2020-08-12
1.2.1 | 3 | Đánh giá và lựa chọn phương pháp phù hợp với nhu cầu ứng dụng. | 2020-08-12 | 2020-08-12 | 100% | Done
1.2.2 | 3 | Vẽ sơ đồ kết cấu và luồng thực thi của ứng dụng. | 2020-08-12 | 2020-08-12 | 100% | Done
1.3 | 2 | Sắp xếp theo bố cục và hoàn thành nội dung. | 2020-08-13 | 2020-08-13
1.3.1 | 3 | Đánh giá tổng quan và tinh chỉnh lại tài liệu. | 2020-08-13 | 2020-08-13 | 100% | Done
1.3.2 | 3 | Bước đầu hoàn thiện tài liệu phân tích thiết kế. | 2020-08-13 | 2020-08-13 | 100% | Done
2 | 1 | Tiến hành huấn luyện các ký tự cần sử dụng trong ứng dụng. | 2020-08-17 | 2020-09-08
2.1 | 2 | Thu thập dữ liệu. | 2020-08-17 | 2020-08-20
2.1.1 | 3 | Đánh giá dữ liệu (theo các yếu tố: tính đặc trưng , phạm vi bao phủ thực tế, . . .). | 2020-08-17 | 2020-08-18 | 100% | Done
2.1.2 | 3 | Tìm kiếm và thu thập các dữ liệu đặc trưng cho bộ dữ liệu kiểm tra. | 2020-08-18 | 2020-08-20 | 100% | Done
2.2 | 2 | Tiền xử lý dữ liệu. | 2020-08-20 | 2020-08-26
2.2.1 | 3 | Loại bỏ dữ liệu trùng lặp. | 2020-08-20 | 2020-08-20 | 100% | Done
2.2.2 | 3 | Sử dụng một số phép biến đổi để tăng dữ liệu phục vụ cho quá trình huấn luyện (hay làm phong phú dữ liệu). | 2020-08-20 | 2020-08-25 | 100% | Done
2.2.3 | 3 | Làm mịn và điều chỉnh kích thước ảnh về đúng với kích thước ảnh mà mô hình sử dụng. | 2020-08-26 | 2020-08-26 | 100% | Done
2.2.4 | 3 | Phân chia theo cấu trúc dữ liệu 60-20-20: tương ứng với 60% dữ liệu huấn luyện, 20% dữ liệu đánh giá, 20% dữ liệu kiểm tra. | 2020-08-26 | 2020-08-26 | 100% | Done
2.3 | 2 | Huấn luyện mô hình. | 2020-08-27 | 2020-09-03
2.3.1 | 3 | Thiết lập cách nạp dữ liệu vào mô hình. | 2020-08-27 | 2020-08-27 | 100% | Done
2.3.2 | 3 | Thiết kế mô hình. | 2020-08-28 | 2020-08-28 | 100% | Done
2.3.3 | 3 | Thiết lập các siêu tham số mô hình (là tham số ảnh hưởng chính đến chất lượng mô hình). | 2020-08-28 | 2020-09-01 | 100% | Done
2.3.4 | 3 | Đánh giá nhanh kết quả. | 2020-09-01 | 2020-09-01 | 100% | Done
2.3.5 | 3 | Tinh chỉnh và thay đổi mô hình trong quá trình huấn luyện. | 2020-09-01 | 2020-09-03 | 100% | Done
2.4 | 2 | Đánh giá khi hoàn thành và lưu mô hình. | 2020-09-04 | 2020-09-15
2.4.1 | 3 | Hiển thị kết quả độ chính xác trên hai bộ dữ liệu đánh giá và kiểm tra. | 2020-09-04 | 2020-09-04 | 100% | Done
2.4.2 | 3 | Đánh giá mô hình dựa trên ma trận nhầm lẫn. | 2020-09-04 | 2020-09-04 | 100% | Done
2.4.3 | 3 | Đánh giá lại mô hình. | 2020-09-04 | 2020-09-07 | 75%
2.4.3.1 | 4 | Quay lại tinh chỉnh mô hình theo kết quả đánh giá. | 2020-09-04 | 2020-09-07 | 50%
2.4.3.2 | 4 | Lưu mô hình nếu đủ điều kiện (ĐK: độ chính xác phải trên 90% và sự sai lệch thực tế không quá lớn, . . .). | 2020-09-07 | 2020-09-07
2.4.4 | 3 | Lựa chọn mô hình và kiểm thử khi chạy thực tế (kiểm tra đối với cử chỉ được trích xuất trong thời gian thực). | 2020-09-08 | 2020-09-08 | 30%
3 | 1 | Tích hợp vào ứng dụng 3DViewer | 2020-09-09 | 2020-09-16
3.1 | 2 | Tìm hiểu và xác định phương pháp. | 2020-09-09 | 2020-09-11
3.2.1 | 3 | Giao tiếp ứng dụng bằng socket sử dụng phương thức TCP | 2020-09-09 | 2020-09-09 | 75%
3.2.2 | 3 | Xây dựng module trong Unity. | 2020-09-09 | 2020-09-10 | 50%
3.2.3 | 3 | TÌm hiểu và lập trình giao diện và xử lý sự kiện trong Unity | 2020-09-09 | 2020-09-11 | 30%
3.2 | 2 | Triển khai code và tiến hành debug. | 2020-09-14 | 2020-09-16
3.2.1 | 3 | Tìm hiểu cấu trúc mã nguồn ứng dụng 3DViewer | 2020-09-14 | 2020-09-14 | 50%
3.2.2 | 3 | Hiển thị màn hình thu nhận ảnh từ webcam trên Unity. | 2020-09-14 | 2020-09-15 | 100% | Done
3.2.2.1 | 4 | Viết module tích hợp của mô hình. | 2020-09-14 | 2020-09-15 | 55%
3.2.2.2 | 4 | Trao đổi và xử lý tín hiệu thông qua giao thức TCP socket. | 2020-09-15 | 2020-09-16 | 80%
3.2.2.3 | 4 | Xử lý các trường hợp ngoài mục đích ứng dụng. | 2020-09-15 | 2020-09-16
3.2.3 | 3 | Kiểm tra các chức năng xem đã hoạt đúng theo yêu cầu. | 2020-09-16 | 2020-09-16
4 | 1 | Viết báo cáo tổng kết. | 2020-09-17 | 2020-09-18
4.1 | 2 | Viết tài liệu báo cáo. | 2020-09-17 | 2020-09-17
4.1.1 | 3 | Tổng hợp, hoàn thiện và chỉnh sửa báo cáo. | 2020-09-17 | 2020-09-17
4.2 | 2 | Soạn slide thuyết trình. | 2020-09-18 | 2020-09-18
4.2.1 | 3 | Tóm tắt kết quả đạt được, bài học rút ra. | 2020-09-18 | 2020-09-18