## WBS & GANTT
FPGA/WBS - tracking list
※ unauthorized use any content in this document is prohibited
Refer to the requirement definition sheet https://cb.brycen.co.jp/cgi-bin/cbag/ag.cgi?page=FileView&ffid=490126
WBS ID | WBS Level | TASK LIST (major tasks: WBS level 1-2, minor tasks: WBS level 3-4) | PROGRESS TRACKING |  |  |  | JULY | [30 empty] | AUGUST | [30 empty] | September
|  |  | start date yyyy/mm/dd | due date yyyy/mm/dd | progress % | status | 2020-07-01 | 2020-07-02 | 2020-07-03 | 2020-07-04 | 2020-07-05 | 2020-07-06 | 2020-07-07 | 2020-07-08 | 2020-07-09 | 2020-07-10 | 2020-07-11 | 2020-07-12 | 2020-07-13 | 2020-07-14 | 2020-07-15 | 2020-07-16 | 2020-07-17 | 2020-07-18 | 2020-07-19 | 2020-07-20 | 2020-07-21 | 2020-07-22 | 2020-07-23 | 2020-07-24 | 2020-07-25 | 2020-07-26 | 2020-07-27 | 2020-07-28 | 2020-07-29 | 2020-07-30 | 2020-07-31 | 2020-08-01 | 2020-08-02 | 2020-08-03 | 2020-08-04 | 2020-08-05 | 2020-08-06 | 2020-08-07 | 2020-08-08 | 2020-08-09 | 2020-08-10 | 2020-08-11 | 2020-08-12 | 2020-08-13 | 2020-08-14 | 2020-08-15 | 2020-08-16 | 2020-08-17 | 2020-08-18 | 2020-08-19 | 2020-08-20 | 2020-08-21 | 2020-08-22 | 2020-08-23 | 2020-08-24 | 2020-08-25 | 2020-08-26 | 2020-08-27 | 2020-08-28 | 2020-08-29 | 2020-08-30 | 2020-08-31 | 2020-09-01 | 2020-09-02 | 2020-09-03 | 2020-09-04 | 2020-09-05 | 2020-09-06 | 2020-09-07 | 2020-09-08 | 2020-09-09 | 2020-09-10 | 2020-09-11 | 2020-09-12 | 2020-09-13 | 2020-09-14 | 2020-09-15 | 2020-09-16 | 2020-09-17 | 2020-09-18 | 2020-09-19 | 2020-09-20 | 2020-09-21 | 2020-09-22 | 2020-09-23 | 2020-09-24 | 2020-09-25 | 2020-09-26 | 2020-09-27 | 2020-09-28 | 2020-09-29 | 2020-09-30
1 | 1 | Làm quen môi trường ở công ty và học kiến thức mới. | 2020-07-20 | 2020-08-07
1.1 | 2 | Làm quen môi trường công ty và đọc các tài liệu hướng dẫn. | 2020-07-20 | 2020-07-24
1.1.1 | 3 | Được cấp tài khoản cá nhân, email nội bộ công ty và các thiết lập cơ bản. | 2020-07-20 | 2020-07-20
1.1.2 | 3 | Triển khai và viết tài liệu cài đặt khóa luận tốt nghiệp lên máy công ty. | 2020-07-21 | 2020-07-22
1.1.3 | 3 | Thực hiện những công việc cần làm khi mới vào EMS. | 2020-07-23 | 2020-07-24
1.2 | 2 | Tìm hiểu và thực hành viết BenchMark cho khóa luận tốt nghiệp. | 2020-07-27 | 2020-08-10
1.2.1 | 3 | Tham khảo tài liệu BenchMark và xác định nội dung trình bày. | 2020-07-27 | 2020-07-27
1.2.2 | 3 | Tiến hành khảo sát và thu thập số liệu. | 2020-07-28 | 2020-07-29
1.2.3 | 3 | Biểu diễn tính toán trên số liệu thu được và đưa ra nhận xét. | 2020-07-30 | 2020-07-31
1.2.4 | 3 | Chỉnh sửa lại BenchMark theo góp ý của trainer và tìm hiểu phương pháp nâng cao chất lượng mô hình. | 2020-08-03 | 2020-08-04
1.2.5 | 3 | Tham gia lễ tiếp đón và đào tạo nhân viên mới. | 2020-08-05 | 2020-08-05
1.3 | 2 | Tìm hiểu cách viết WBS | 2020-08-06 | 2020-08-07
1.3.1 | 3 | Lên ý tưởng và viết nội dung cần thực hiện vào WBS. | 2020-08-06 | 2020-08-06
1.3.2 | 3 | Chỉnh sửa WBS và bổ sung biểu đồ GANTT. | 2020-08-07 | 2020-08-07